Legit Flow — Kế hoạch Demo (3 ngày) + Roadmap 4 tháng (On‑prem Kubernetes)

Information Assurance + Business Plan
Ngày lập: 24/02/2026

Confidential — For evaluation purposes only

# 1. Mục tiêu & phạm vi

Mục tiêu: (1) dựng demo luồng sản phẩm trong 3 ngày (24–26/02/2026), (2) hoàn thiện khung dự án và đạt trạng thái MVP 'sơ bộ sử dụng được' trong 4 tháng (đến 30/06/2026), để có đủ thời gian hardening và chuẩn bị demo trước hội thảo doanh nghiệp giữa tháng 8/2026.

Phạm vi MVP (4 tháng):

On‑prem K8s package (Helm/GitOps), hardened-by-default (non-root, read-only FS, NetworkPolicy, mTLS).

Data Plane: Intercept → Classify (risk tier) → Sanitize (utility-preserving) → Route (SLM/LLM on-prem) → Output Guard (stream-safe).

Audit 2-tier: metadata always-on + nội dung đã biến đổi; break-glass workflow.

Policy-as-code + versioning + approval (MVP UI).

Tool/Action Guard (Phase-1) cho các tác vụ có thể gây hậu quả thực thi.

Test framework + dataset plan để chứng minh KPI PoC: Zero structured exfiltration + auditability.

# 2. Flow chart (luồng sản phẩm)

# 3. Gantt chart tổng thể

Ghi chú: mục tiêu 'MVP usable' hoàn thành 30/06/2026. Tháng 7–giữa tháng 8 dành cho hardening, tài liệu kỹ thuật, kịch bản demo, và sales enablement.

# 4. Kế hoạch làm demo luồng sản phẩm trong 3 ngày (24–26/02/2026)

Mục tiêu demo 3 ngày: chạy được core path end-to-end để trình diễn các điểm khác biệt:

Intercept request từ app demo → Legit Flow → on‑prem LLM endpoint (mock hoặc model nhỏ).

Layer 1 hard rules: nhận diện & xử lý Structured PII/Secrets (mask hoặc block theo policy).

Streaming output guard: holdback cửa sổ nhỏ + truncate an toàn khi vi phạm (không buffer toàn bộ).

Audit Tier 1 metadata always-on; Tier 2 lưu bản đã redacted/pseudonymized.

Policy config YAML + hot reload (MVP), sẵn sàng nâng cấp sang approval UI ở sprint sau.

Kế hoạch theo ngày (deliverables cụ thể):

| Ngày | Mục tiêu kỹ thuật | Deliverables | Test/Check | Owner (gợi ý) |
| --- | --- | --- | --- | --- |
| Day 1 — 24/02 | K8s skeleton + dataplane intercept/route | Helm chart skeleton; demo app → proxy → LLM mock; basic metrics | helm install smoke; request/response OK; p95 baseline | DevOps + Backend |
| Day 2 — 25/02 | L1 detector + streaming holdback prototype | Regex VN (CCCD/SĐT/email/STK) + secrets; output guard chunking | unit test regex; streaming demo: no raw leak | Backend + QA |
| Day 3 — 26/02 | Audit 2-tier + demo script | Metadata audit; content redacted sample; demo runbook + slides outline | E2E test; verify logs; negative tests (PII/secret) | Backend + PM/Presales |

Tiêu chí demo 3 ngày (Pass/Fail):

Pass: Structured PII/Secrets bị mask/block đúng policy; không xuất hiện trên UI khi ở chế độ block.

Pass: Streaming có holdback tối thiểu; khi vi phạm hệ thống truncate + trả thông báo an toàn.

Pass: Audit Tier 1 ghi đủ who/when/policy/action; Tier 2 không lưu raw với case Restricted.

Fail: Lộ raw PII/secret trên UI trong kịch bản bị block; hoặc gateway crash dưới tải nhẹ.

# 5. Roadmap 4 tháng (24/02 → 30/06/2026) để MVP usable

Chia theo workstreams để triển khai song song:

## WS1 — Platform/DevOps

Helm/GitOps packaging; hardened-by-default profiles; internal CA/mTLS; egress allowlist; offline updates.

Observability: Prometheus/Grafana + structured logs; alert hooks.

CI: lint/test/container scan + helm smoke.

## WS2 — Data Plane Core

Intercept (REST + streaming), auth (JWT/SSO integration stub), rate limit/backpressure.

Router: on‑prem SLM/LLM endpoints; routing policy; retry/circuit breaker.

## WS3 — Detection/Transformation

L1 hard rules: VN regex library + secrets patterns; actions allow/redact/tokenize/block.

Utility‑preserving transforms: generalization + consistent pseudonyms + synthetic replacement (MVP set).

L2 contextual classifier (SLM) on‑prem: warn/flag/escalate (không chặn mặc định).

## WS4 — Output Guard (Streaming-safe)

Sliding window holdback; fast scan per chunk; escalation to slow scan only when needed/tier high.

Truncate + safe substitution; regen under stricter policy; replay-safe logging.

## WS5 — Governance/Audit/Approvals

Policy-as-code, versioning, staged rollout (dev→uat→prod), rollback.

Audit 2-tier + break-glass (2-person rule, ticket link, time-bound).

RBAC/ABAC + separation of duties.

## WS6 — Tool/Action Guard (Phase-1)

Allowlist tool endpoints; scope by role; approvals for sensitive actions; default read-only.

Negative tests: injection→action blocked.

## WS7 — QA/Testing & Dataset

Unit tests; integration tests (helm, policy reload, audit emit); perf tests (k6/locust).

Security tests: SAST/deps scan/container scan; K8s baseline checks.

Dataset: golden + synthetic generator; labeling guide; evaluation reports.

# 6. Tiêu chí cần đạt & thang đo chấm điểm (PoC/MVP)

Chấm điểm 0–5 theo từng tiêu chí; tổng điểm theo trọng số. Mục tiêu: MVP ≥ 75/100 để demo enterprise, ≥ 85/100 để sẵn sàng PoC ngân hàng.

| Tiêu chí | Trọng số | Mục tiêu | Thang đo/Verification | Điểm (0–5) |
| --- | --- | --- | --- | --- |
| Structured PII/PCI/Secrets (L1) — Zero Exfiltration | 20 | Không lọt dữ liệu định dạng chuẩn qua output/log (Restricted). | Leakage rate = 0 trong bộ test chuẩn; unit tests ≥ 95% pass. |  |
| Streaming-safe Output Guard | 15 | Holdback window hoạt động; truncate đúng; không lộ token nhạy cảm. | E2E streaming tests; regression suite. |  |
| Latency/Throughput (p95) | 15 | p95 tăng thêm theo tier nằm trong ngân sách; scale-out ổn định. | Load test 1k/5k concurrency (mô phỏng). |  |
| Audit 2-tier + Break-glass | 10 | Tier1 always-on; Tier2 redacted; break-glass có phê duyệt và truy vết. | Audit integrity checks; access tests. |  |
| Deployability (Hardened K8s) | 10 | Non-root, read-only FS, NP deny-by-default, mTLS; helm install/upgrade/rollback. | Helm smoke + kube policy checks. |  |
| Policy-as-code + Versioning | 10 | Policy changes có version, review, staged rollout. | Policy regression tests. |  |
| Tool/Action Guard | 10 | Allowlist+RBAC+approval cho action nhạy cảm; default read-only. | Negative tests: injection→action blocked. |  |
| Observability & SIEM integration | 10 | Dashboard usage/risk; webhook/SIEM events; alert rules. | Alert firing tests; log schema validation. |  |

# 7. Testing plan (unit / integration / performance / security)

## 7.1 Unit tests

Detector L1: test vectors cho CCCD (12 số), SĐT VN, email, STK; secrets patterns (JWT-like, API keys).

Transformer: generalization/pseudonym/synthetic mapping consistency (same entity → same token in session).

Streaming guard: chunk boundaries, holdback window, truncate behavior, regen logic.

Policy engine: parsing, precedence, default deny/allow, versioning semantics.

Mục tiêu: coverage ≥ 80% core modules; critical detectors/guards ≥ 90%.

## 7.2 Integration & E2E

Helm install/upgrade/rollback smoke trên kind/k3s + (tuỳ) OpenShift compat checks.

E2E: app demo → legitflow → llm mock; verify streaming + audit tier1/2.

SSO/JWT stub integration test; SIEM webhook test (schema + auth).

## 7.3 Performance

Load test (k6/locust): đo p50/p95/p99 latency theo tier; throughput; error rate.

Soak test 4–8 giờ: memory leak, backpressure, log volume.

Resource profiling: CPU/GPU pools cho slow-path classifiers.

## 7.4 Security checks

SAST + dependency scan + container image scan (CVE gating).

K8s hardening: non-root, read-only, seccomp/AppArmor, NetworkPolicy tests.

Secrets management: no secrets in repo; integrate KMS/HSM hooks.

Audit tamper-evidence (hash chain/WORM option) verification.

# 8. Dataset & khung nghiên cứu thuật toán (VN context)

Mục tiêu: chứng minh chất lượng phát hiện (precision/recall) theo từng nhóm dữ liệu và đảm bảo không phá utility.

## 8.1 Dataset plan

Structured PII/PCI/Secrets: bộ test định dạng chuẩn (synthetic) + edge cases (dấu cách, dấu chấm, format cũ).

Vietnamese contextual PII: câu tự nhiên có tên/địa chỉ/chi nhánh; focus giảm false positive bằng policy tier.

Confidential-doc classification: tập mẫu tài liệu nội bộ (đã ẩn danh) + nhãn Public/Internal/Confidential/Restricted.

Prompt injection corpus: mẫu jailbreak phổ biến + biến thể (encoding, lồng ngôn ngữ) để kiểm tra reduce-impact.

## 8.2 Evaluation metrics

Precision/Recall/F1 theo từng label (PII/Secrets/Confidential).

Leakage rate (input/output/log) theo tier: Restricted target = 0 cho structured identifiers.

Utility score (human eval): output vẫn hữu ích sau transform (thang 1–5).

Latency delta theo tier (p95) và cost impact (CPU/GPU).

## 8.3 Algorithm research track (pragmatic)

Baseline: regex + dictionaries (fast-path) + deterministic rule engine.

Contextual layer: SLM classifier on‑prem cho flag/warn; only escalate for tier high.

NER/semantic scan chỉ chạy slow-path và sampling (QA), tránh nghẽn dataplane.

Synthetic replacement: generator giữ format nghiệp vụ nhưng thay số liệu/định danh; kiểm thử consistency.

# 9. Lịch họp đánh giá dự án (mỗi Thứ 6 đến đầu tháng 4/2026)

Mục tiêu: review theo KPI (leakage/latency/FP) và chốt backlog tuần.

| Ngày (Thứ 6) | Nội dung bắt buộc | Artifacts nộp | Quyết định |
| --- | --- | --- | --- |
| 27/02/2026 | Demo sprint + KPI + rủi ro + thay đổi policy | Sprint report, test results, risk log, updated gantt/backlog | Go/No-go; scope adjustment; assign owners |
| 06/03/2026 | Demo sprint + KPI + rủi ro + thay đổi policy | Sprint report, test results, risk log, updated gantt/backlog | Go/No-go; scope adjustment; assign owners |
| 13/03/2026 | Demo sprint + KPI + rủi ro + thay đổi policy | Sprint report, test results, risk log, updated gantt/backlog | Go/No-go; scope adjustment; assign owners |
| 20/03/2026 | Demo sprint + KPI + rủi ro + thay đổi policy | Sprint report, test results, risk log, updated gantt/backlog | Go/No-go; scope adjustment; assign owners |
| 27/03/2026 | Demo sprint + KPI + rủi ro + thay đổi policy | Sprint report, test results, risk log, updated gantt/backlog | Go/No-go; scope adjustment; assign owners |
| 03/04/2026 | Demo sprint + KPI + rủi ro + thay đổi policy | Sprint report, test results, risk log, updated gantt/backlog | Go/No-go; scope adjustment; assign owners |

# 10. Risk register (top 10) & mitigation

| Rủi ro | Giảm thiểu | Owner |
| --- | --- | --- |
| Latency tăng do scan ngữ cảnh | 2-stage pipeline; slow-path only; perf budgets; profiling. | PM/Tech Lead |
| Streaming leak token nhạy cảm | holdback window + truncate; Restricted tier stricter; E2E tests. | PM/Tech Lead |
| False positive cao (VN) | Observe/Coach first; dataset tuning; tiered policy; allow exceptions. | PM/Tech Lead |
| Audit store trở thành honeypot | 2-tier; redacted by default; break-glass; tamper-evident; SoD. | PM/Tech Lead |
| K8s hardening incompatibility | non-root/read-only; manifests for OpenShift; offline updates; signed releases. | PM/Tech Lead |
| Tool/agent gây hậu quả thực thi | tool guard phase-1; allowlist; approvals; read-only default. | PM/Tech Lead |
| Sales cycle dài → thiếu runway | paid pilot + PS revenue; expand ICP (gov/health/telco) for cashflow. | PM/Tech Lead |
| DIY cạnh tranh | sell Day-2 ops: governance, audit, approvals, reports, VN packs. | PM/Tech Lead |
| Dataset hạn chế | synthetic generator; on-prem labeling; privacy-safe sampling. | PM/Tech Lead |
| Scope creep | strict MVP; Friday governance; change control. | PM/Tech Lead |